## Work Plan FY25
SOUTHEAST REGIONAL ELDERCARE COALITION WORKPLAN FY23-26 UPDATED January 2025
Quarter | Staff | Deliverable | Tasks | Timeline | Notes - Dec 2024 and prior
3rd QRT FY23
12/1/22- 3/31/23 | JEDC Hiring Team and SREC Steering Committee | Hire Program Director | JEDC will recruit, hire and onboard a new Program Director to be housed at JEDC with an empowered SREC Steering Committee that will provide eldercare expertise. PD may engage in a retreat with JEDC staff and SREC Steering Committee. | Hire: Dec 1, 2022 | Program Director Tonya Muldoon hired July26, 2023
12/1/22- 3/31/23 | Program Director | 1. Hire Staff 2. Initiate Research 3. Website | 1. Recruit, hire and onboard new staff. Negotiate co-location of staff with relevant agency and continue weekly check-ins regarding status. Program Director reporting monthly to Coalition of the whole and supporting committee structure 2. Initiate research into Best Practices Eldercare Model, employer survey of Coalition Members to inform navigational tool and Navigational Tool outline. 3. Maintain Website as Communication vehicle 4. Work with Steering Committee to develop contracts between Provider and Client with family involvement where appropriate. 5. Initiate research development of wage supp program (who, what, when, where, how, monitor for appropriate use, etc.) | 1. Staff Onboard by 3/31/22 2. Completed by 3/31/22 3. Ongoing 4. Complete by 3/31/22 5. Initiate Wage Supp by 4/1/23 | Tess Rouse, Recruiter hired March 26, 2024 Interviewed three Navigator, none trainer
12/1/22- 3/31/23 | Recruiter | Coordinate with AKDOL | Begin training process as Recruiter using AKDOL and other desired services and mechanisms. Emphasize DSP recruitment initially. Develop processes for Coalition Members to submit staffing requests to Recruiter for all levels of positions. | Ongoing. Report weekly to Program Director. | Staff was not hired until March 26.
12/1/22- 3/31/23 | Trainer | Coordinate with SERRC and UAS and other training entities | Develop model of training opportunities to present to applicants that highlight advancement and ongoing career opportunities. Support initiation of the PATH Academy. Begin training process with early emphasis on DSP providers. Work closely with Recruiter for referrals from training. | Ongoing. Report weekly to Program Director. | Trainer was not able to be obtained. This is in part due to determining the level of trainer needed for the DSP education. Most cases a nurse would be needed. DSP declined support.
12/1/22- 3/31/23 | Navigator | Coordinate with SAIL | Work with Program Director to develop Navigational Tool to be used by providers and clients to be housed on website and updates quarterly by Navigator. Begin meeting with providers and clients once navigational tool is in place and training completed. Develop a referral mechanism to Navigator from Coalition members. | Ongoing. Report weekly to Program Director. | Teal Street office was opened in November 2023. Hiring of a navigator did not occur. Three interviews however candidates did not have the proper degree of experience.
4th QRT FY23
4/1/23- 6/30/23 | Program Director | Program Management | 1. Report results of regional Employer survey to Coalition Members and introduce Navigational Tool. 2. Maintain website as Communication Vehicle. 3. Implement onsite contracts between Provider and Client with family involvement where appropriate. 4. Initiate wage supp program (who, what, when, where, how, monitor for appropriate use, etc.). 5. Supervise staff and continue weekly check-ins regarding status. 6. Staff to report monthly to the Coalition and supporting subcommittees. 7. Begin preparations for the FY24 Summit to be delivered in 2023/2024. 8. Begin Fiscal Year Two Work Plan to be completed by 7/1/23. | 1. Ongoing. Weekly meeting with staff Monthly report to the Steering Committee 2. Ongoing 3. TBA 4. TBA 5. Ongoing 6. Monthly 7. 2023/2024 8. By 7/1/23 | 1. Done, Survey was a flop with limited responses and invalid information. 2. Website is updated monthly. Ongoing 3.Provider and Client agreement has been drafted but as project has changed not being accessed. 4. Attempted to implement wage supplementation program, DSP agencies have declined to support the project as originally drafted. They then despite feedback did not agree with the second drafting of the project and refused to engage. Now of the third major shift in programing, the agencies are still not in support of training for hire or national certification. 5. Ongoing. 6. Done. Ongoing 7. Started, Ongoing 8. Done
4/1/23- 6/30/23 | Recruiter | Teal Street Center | 1. Continue dedicated Recruiter activities using all available resources, emphasizing DSP recruitment. 2. Report on success/proposed modifications of processes for Coalition 3. Members to submit staffing requests to Recruiter for all levels of positions. | Ongoing. Report weekly to Program Director | 1-2. Recruiter position, has been supporting the development of the Summit and the Navi Tool while researching job fair locations and workforce resources. 3. Referrals for the recruiter will be active following training with CCS pilot.
4/1/23- 6/30/23 | Trainer | Teal Street Center | 1. Path Academy should be fully operational, and Trainer will work closely with Recruiter for referrals for training, as well, as coordinate with other training entities that can provide focused DSP Training in the region. | Ongoing. Report weekly to Program Director. | 1. Promoted PATH through the Coalition network and posted at TEAL Street. Provided support for mock interviews. SREC Project provided a MOA for food insecurities to he used for in-class meals and snacks.
4/1/23- 6/30/23 | Navigator | Teal Street Center Navigational Tool | Navigational Tool should be operational and used for providers and clients to be housed on website and updated quarterly by Navigator. | Ongoing. Report to Program Director. Roll out 8/1/24 | ongoing development
1st QRT FY 24
7/1/23- 9/30/23 | Program Director | Program Management | Present Fiscal Year End Report to Coalition Steering Committee and recommendations for Year Two Work Plan. Use recommendations of Steering and Full Coalition to enhance, modify, improve elements of service provision by all staff. | Report in July 2023 to Steering Committee and full coalition re: Work Plan | Completed by Brian Holst and Charla Brown, Tonya Muldoon, PD has just been hired.
7/1/23- 9/30/23 | Recruiter |  | Present Fiscal Year End Report to Coalition Steering Committee and recommendations for Year Two Work Plan | Report Weekly to Program Director. | N/A - Completed by Brian and Charla
7/1/23- 9/30/23 | Trainer |  | Present Fiscal Year End Report to Coalition Steering Committee and recommendations for Year Two Work Plan | Report Weekly to Program Director. | N/A - Completed by Brian and Charla
7/1/23- 9/30/23 | Navigator |  | Present Fiscal Year End Report to Coalition Steering Committee and recommendations for Year Two Work Plan | Report Weekly to Program Director. | N/A - Completed by Brian and Charla
2nd QRT FY 24
10/1/23- 12/1/23 | Program Director |  | Objectives and Activities to be determined via strategic planning and assessment of activities. | 1. Ongoing | Redrafted program, worked to meet DSP agency to determine partnership and buy in for services.
3rd QTR FY 24 | Updated Work Plan November 2024
12/1/23- 3/31/34 | Program Director | Hire Staff: Navigator and Recruiter | 1. JEDC will recruit, hire and onboard new staff for navigation and recruitment tasks. Staff will be housed at Teal Street Center and the DOL Office with rotation to the JEDC main office. Staff will have weekly check-ins regarding status. 2. Program Director reporting monthly to Coalition of the whole and supporting committee structure. 3. Maintain Website as Communication vehicle 4. Work with Steering Committee to develop contracts between Provider and Client with family involvement where appropriate. 5. Initiate research development of wage supp program (who, what, when, where, how, monitor for appropriate use, etc.) | 1. Staff Navigator and Recruiter Onboard by 3/31/24 2. Ongoing Monthly | 1. Feb Offer made to Theresa Rouse for the recruiter position Accepted and started March 26, 2024 She came form DOL and discussed options for office space. Preference was to coordinate through Teal Street Office vs DOL office. 2. Ongoing
12/1/23- 3/31/24 | Program Director | Website Contact | Maintain SREC website as Communication vehicle. | Ongoing | Continued ongoing
12/1/23 - 3/31/24 | Program Director | Hire/contract a Web Developer Navigation Tool (website) | 1. JEDC will contract or/ recruit and hire a web developer/web designer to assist with the creation of a navigation tool. 2. Coordinate a work group of Coalition and Steering Committee members to assist with the development of a navigational tool content and functionality. 3. Research and order tablets for use at the Senior Centers and with DSP for accessing the Navigational Tool. | 1. Contract /hire by 3/31/24 2. Group created by 3/31/24 3. Place the order by 3/31/24 | 1. SREC staff have been access web design skills internally through a contract with Bear Star. 2. Development continues. Feedback has been taken from SC and Coalition. They however have not been actively engaged with the development through a sub-committee. Offer was made multiple time to each for support, however none has been provided support to participate in a sub-committee. 3. Request was sent to Hansen and Gress. Quoted. The pilot with CCS has been developing. Tablets have not yet been purchased for the project. 2025 - Tablets are not being perused.
12/1/23- 3/31/24 | Program Director | Senior Centers | 1. Coordinate with CCS and Hansen Gress (IT) to determine best equipment to use in the region. Agreed to experiment with two different models. 2. Determine best option, order equipment, training staff. 3. Set up Senior Center staff on Relais system for tracking training. | 1. By 1/31/24 2. Target by 3/31/24 (likely by 6/30/24) 3. By 3/31/24 roll out of training will be by 6/30/23. | 1. HG order NEAT system for testing - not yet obtained Feb 2024 April - obtained a small NEAT system product to review in office at CCS. This was not a product that a could be sent to a village to try. Example was returned to NEAT. They have to be purchased for a trial due to shipping costs. 2. NEAT system is best for cost and flexibility. Reviewed multiple options. 3. Relais - still working with Senior Center for review of programing from SREC for a possible pilot.
12/1/23- 3/31/24 | Program Director | Relais Contract (Training) | 1. Finalize initial contract with Relais platform. 2. Work with Relais on website platform for training tracking. 3. Maintain close contact with Max at Relais for class library changes. 4. Notify Relais on Summit plan. Extended invite for them to attend the event in Fall 2024. | 1. Contract in place 1/31/24. 2. Establish training platform structure within Relais for tracking. Estimated 6-8 weeks to complete with Relais specialist by 3/31/24. 3. CPR portion may be added later then the initial training package. (determine by 3/31/24). 4. Ongoing. Maintain contact with Relais staff to help coordinate for the event. | 1. Delayed due to DSP agency lack of participation. 2. Relais quotes in hand. DSP have declined training options. PG has worked with Relais to set up options. May still utilize for CPR/First Aid. 3. PD and Relais staff have had min. monthly contacts. 4. Extended offer. unknown if possible... will likely depend upon contract.
12/1/23- 3/31/24 | Program Director | CPR/First Aid (Training) | 1. Obtain contacts for regional EMS Chiefs. 2. Determine BLS instructor availability in each community. 3. Determine the number in need of renewal training and initial BLS Instructor Training. Aiming min of two per community. 4. Establish plan with SEREMS for BLS Instructor training. 5. Establish contract for CCS and DSP's new hires to have BLS Instructors available for future skills check. 6. Contract between EMS Chief and CCS for training sign off agreement in trade for training costs supplement. | 1.-3. By 3/31/24. 4. Determine travel expense and cost for offering class, class size etc. 5. By 3/31/24. 6. Coordinate with Erin Walker-Tolles regarding need for formal contract to be established (may help with CPR Skills Sign off waver process to have contract established). | 1. Some contact was made to EMS providers. All did not respond. Need is there in smaller communities. 2. Contact was established with SREMS, Thor American Heart Instructor Trainor is available to provide classes at the Summit, Travel and $200 per student is required. 3. Could not be determined 4. Done 5. Determined that the availability of CPR/First Aid is different in each community. the HUB are accesses private paid CPR instructors or on-line only instruction. Villages and local business are utilizing the American Heart. Tides ESQ has need and likely other agencies locally. Still to be determined. 6. May consider with application for Summit training.
12/1/12- 3/31/24 | Program Director | Coordinate with UAS (Training) | 1. Determine availability and wiliness of UAS faculty to work to establish a polit DPS hands-on training for possible use with an apprenticeship and/or just regional access. 2. Determine delivery of instruction to rural Alaska students. 3. Determine if all or part of class could be included with Summit Training. | 1. By 3/31/24. 2. By 3/31/24 or with completion of Senior Center technology. 3. By 3/31/24, to be determined by design, availability, and feedback by UAS staff. | 1. UAS on Class, SDS Certification started May 2024 ending June 27 2024. 2. UAS has been approved by DSDS for instruction Feb 2024. Hybrid model developed. Two optional weeks of hands-on education and five weeks on online learning. 3. Can not be included in Summit. Too long of a required course.
12/1/23 - 3/31/24 | Program Director | Coordinate with SERRC regarding PATH Academy (Training, Agency support) | 1. Coordinate payment to SERRC to help with student food insecurities. 2. Coordinate recruiter to visit communities to help promote PATH Training through Job Fairs as possible. | 1. By 1/1/24 Payment to SERRC. 2. PATH Class Schedule January in Juneau February in Ketchikan April in Yakutat Unknown for 2025 classes | 1. Agreement in place with SERRC for food items, SREC PD has participated in PATH Mock interviews and encouraged businesses participate as support for program 2. Ongoing likely following Summit - Spring 2025
12/1/23- 3/31/24 | Recruiter | Coordinate with DOL | 1. Begin training process as Recruiter using AKDOL and other desired services and mechanisms. Emphasize DSP recruitment initially. 2. Develop processes for Coalition Members to submit staffing requests to Recruiter for DSP positions. 3. Identify Job and Career Fairs occurring with high school and college student focus. 4. Coordinated with other agencies to developed job healthcare options for the regional school districts, in-person and possible virtual. | 1. Ongoing report weekly to Program Director. 2. Process to be developed by 3/31/24. 3. By 3/31/24. 4. Set up meeting with agencies of interest, SEARHC, Bartlett Regional Hospital, PATH, EMS, UAS etc. | 1. PD has provided general education and information training as we develop together the program design. Original plan for SREC has changed and the recruiter is not accessing AKDOL at this time due to DSP agency decline for assistance with direct recruitment. 2. Program change. With the development of the Triage Navigational training and support through CCS, referrals will be able to be made for informational support by the Recruiter. 3. Recruiter has developed a list of regional job fairs and is continuing to monitor for more opportunities. 4. Researching some on topic. Will need additional time to determine options.
12/1/23- 3/31/24 | Navigator | Coordinate with SAIL | 1. Work with Program Director to develop Navigational Tool to be used by providers and clients to be housed on website. 2. Updated website quarterly by Navigator. 3. Coordinate with SAIL regarding option to send faxes if needed or scan HIPAA sensitive documents. 4. Determine ROI for SREC to use for coordination of elder services. - possible need to contract a lawyer. 5. Begin meeting with providers and clients once navigational tool is in place and training completed. 6. Develop a referral mechanism to Navigator from Coalition members. 7. Develop training for NAVI Tool for Summit and community access. | 1. Ongoing 2. Ongoing 3. By 3/31/24 4. By 3/31/24 5. By third quarter, September 2024 6. By 3/31/24 7. By Third Quarter, September 2024 | 1. Update Feb 2024 min support on project without a great deal of support to develop the tool. K.A. of the JCOA has volunteer to assist June 2024, KA only visited once on the project and did not return. 2. Development is continued 3.-4. Not applicable to the changes being made in the Project plan. 5. Target Aug - Sept 2024 6. Target Sept 2024, Increased need for the Senior Centers to also have training developed and Triage Section added to the Navi Tool.
12/1/24- 3/31/24 | Program Director | Teal Street Center | 1. Maintain presence at Teal Street weekly while developing staff, 2. Maintain updated information of current events, training, options 3. Develop referral process as noted in other sections this quarter 4. Continue to coordinate through Cagney (JEDC) to obtain phone communications at Teal Street Office. | 1. Ongoing, until staff is able to manage 2. Ongoing 3. Variable completion 4. Office will not be open regularly or published until phone services can be obtained.(safety concerns and practical office functioning) | 1. Feb 2024 update - still no phone or camera for computer April, computer and phone established at Teal Street. Staffed weekly with as needed appointment available. 2.Recuiter is updating information, PD is also seeking information via the Coalition to manage. 3. Will be developed with Triage Navigational Training for Senior Centers. 4. Done
12/1/24- 3/31/24 | Program Director | Summit | 1. Determine date for Summit. SC voted for a Fall Summit. Looking at Oct. or Nov dates 2024 2. Coordinate a work group of Steering Committee and Coalition members to help provide feedback and coordination for the planning of a regional Summit. 3. Notify Coalition members of date. 4. Send out Save the Date flyers region wide through coalition. | 1. By 1/1/24 2. By 12/31/23 3. Once date is determined. 4. Once date is determined. | 1. Feb 2024 update, Fall Summit - Oct 1-2 2. Steering Committee and support planning occurring 3. Verbally notified Coalition in February of tentative dates for Summit. Save the Date went out June 2024 4. Save the Date went out June 2024
12/1/23- 3/31/24 | Program Director | Coordinate with Steering Committee and Coalition | 1. Coordinate a work group of Steering Committee and Coalition members to help provide feedback and coordination for the planning of a regional Summit. 2. Program Director to meet with JACC to contract for the rental of the Centennial Hall 3. Create a theme for the Summit 4. Send out Save the Date Flyer and information to regional contacts, post on social media, community calendar, radio etc. Purchase poster service through the JACC. 5. Establish system for venders to sign up for Summit. Contact targeted community venders with special invitation. 6. Determine availability and variety of food venders (coffee, breakfast foods, lunch). 7. Determine class offerings, contact possible speakers. 8. Order give away for SREC/JEDC with logo 9. Obtain supplies for the event - name tags, pens etc. 10. Create "certificate of training" documents - determine process to provide to conference participants. 11. See if DBA / agencies would donate door prizes to participants. 12. Determine process and promote to agencies for rural/village scholarships to the Summit, process payments to agencies. 13. Determine what participants will receive upon arrival - class schedules, pens, bags etc. 14. Determine registration process - possible ticketing 15. Book hotel room blocks as possible for the event. | 1. By 12/31/23 2. Appointment scheduled for 1/6/24 3. With Coalition subcommittee by 1/30/24 4. Once date can be determined. 5. By 3/31/24 6. By 3/31/24 7. Develop list of contacts by 3/31/24 and start process of securing speakers by 6/30/24 8. By 5/31/24 9. By 5/31/24 10. Have draft created by 3/31/24 11. Assign to Stacey at JEDC to see what options there may be, have feedback by 6/30/24. 12. By 3/31/23 - get information out to agencies once date is determined. 13. By 6/30/24 order should be created. 14. By 3/31/24 15. By 1/30/24 | 1. Two groups developed, Content and Logistics 2. Done, ongoing meeting until Summit date 3. Connecting the Community, Done 4. Save the Date flyer sent June to coalition, SC, Facebook, Twitter, website, etc. 5. PD has requested direction on ticketing of the Summit since January 2024, without response then use another product. Uplifter now being considered June 2024. Venders have been offered as speakers have been sot. 6. Have multiple quotes for food venders. Pending additional information for non-catered food options. Picked Red Ceder Catering. 7. 6\2024 Developing still. developed and requested sent in July 2024. 8. Have quotes pending final decision. Logo was not completed until April 2024. June finalized 9. pending 10. Pending the finalization of the Agenda for the Summit. 11. Undetermined 12. Developing application process to use for Summit Travel, Hiring and retention bonus 13. Pending - have quotes for swag 14. Meeting scheduled for June 28 and follow up meeting pending for July to access Uplifter. 15. Block of hotel rooms have been booked.
12/1/23- 3/31/24 | Program Director | Logo - media | 1. Design a logo for SREC Coalition/Summit - or maintain current - TBD with Steering Committee 2. Re-create brochures with logo | 1. Logo design determined by 3/31/24 or TBD 2. TBD | 1.Feb 2024 Spoken with Brian, He is to sent the logo to Ceder Group to have it recreated. PD provided SREC Steering Committee with ideas but they resisted a change in the moment and suggested the access to a professional designer to make altercations. Issued Logo April 2024 2. Pending program changes, completed new brochures Sept 2024.
4th QTR FY 24
4/1/24- 6/30/24 | Program Director | Staff Management | 1. Implement onsite contracts between Provider and Client with family involvement where appropriate. 2. Supervise staff and continue weekly check-ins regarding status. 3. Report monthly to Coalition and supporting committee structure. 4. Begin Fiscal Year Two Work Plan to be completed by: | 1. Ongoing 2. Ongoing 3. Monthly ongoing 4. July 1, 2024 | 1. Set with original program design and is not being utilized at this time. 2. Done 3. Done 4. Pending change in project, Updated June 2024 and Jan 2025
4/1/24- 6/30/24 | Recruiter | Teal Street | 1. Continue dedicated Recruiter activities using all available resources, emphasizing DSP Recruitment. Identifying job fairs and local events to promote workforce. 2. Report on success / proposed modifications of processes for Coalition 3. Members to submit staffing positions to Recruiter for all levels of positions. Recruiter will post job opening on Navi Tool and Website, social media etc. 4. Work with Clients at Teal Street Center/DOL through walk-in or by appointment. Support education/employment referral or referral for benefit support. 5. Continued development of the Navigational Tool. | 1. Ongoing 2. Monthly 3. Ongoing 4. Ongoing 5. Until Complete, Target by 8/30/24 | 1. Goal established with original recruiter design and is not being utilized at this time. 2. . Monthly 3. Posted on Navi Tool. Only 2 DSP agencies are hiring actively. They have declined to provide openings. 4. Ongoing 5. Ongoing
4/1/24- 6/30/24 | Navigator Program Director | Teal Street | 1. Continued development of the Navigational Tool. 2. Work with clients at Teal Street Center through walk-in or by appointment. Support education/employment referral and assistance with benefits. 3. Dedicated Navigator activities to locate regional events and/or services for posting on the Navi Tool and SREC website. | 1. Until complete, Target by 8/30/24 2. Start once trained 3. Ongoing | 1. Navigator was not hired, PD acting; ongoing development 2. Pending with Triage Navigational Education with the Senior Centers. 3. Ongoing
4/1/24- 6/30/24 | Program Director | Summit | 1. Determine class offerings, contact possible speakers. 2. Order "give aways" with SREC/JEDC logo 3. Obtain supplies for the event - name tags, pens etc. 4. Create "certificate of training" documents - determine process to provide to conference participants. 5. See if DBA / agencies would donate door prizes to participants. 6. Determine what participants will receive upon arrival - class schedules, pens, bags etc. 7. Set up recreational activities 8. Meet with subcommittee of Coalition for suggestions and assistance. | 1. Develop list of contacts by 3/31/24 and start process of securing speakers by 6/30/24 2. By 5/31/24 3. By 5/31/24 4. Have draft created by 3/31/24 5. Assign to Stacey at JEDC to see what options there may be, have feedback by 6/30/24. 6. Order items by 6/30/24. 7. TBD 8. TBD | 1. Speakers are actively being secured. Agenda is not fully completed yet. Pending 2. Quotes have been obtained. Pending review of budget and - no-cost extensions for final budget to order items. 3. Started list 4.Katleen working on sponsor packet 5. see 4. 6. swag quotes obtained. 7. Waving this goal. 8. Bi-weekly meeting occurring with sub-committees regarding Summit planning.
4/1/24- 6/30/24 | Program Director | Senior Center | Roll out dementia training to Senior Center staff. | By 6/30/24 | Pending due to change in project design Nov 2025 provided Senior Center staff with access to Relais training. Dementia and hand on training available for all staff with open library to access information. Contract was secured with CCS.
4/1/24- 6/30/24 | Program Director | Website Contact | Maintain SREC website as Communication vehicle. | Ongoing | Ongoing monthly or as needed
1st QRT FY 25
7/1/24- 9/30/24 | Program Director | Program Management Navi Tool | 1. Present Fiscal Year End Report to Coalition Steering Committee and recommendations for Year Two Work Plan. Use recommendations of Steering and Full Committee to enhance, modify, improve elements of service provision by all staff. 2. Have a functional Navigational Tool for trials. 3. Have a functional Navigational Tool for public access. | 1. Report in July to Steering Committee re Work Plan and present to July Full Coalition 2. By 8/30/23 3. By 9/30/23 | 1. Reported to the SC status of the funding from MACP. 2. Had NAVI tool developed but not fully functional. SC and JEDC leadership, did not focus energy on the release or promotion of the Navi Tool website. Was not promoted at the Summit, as originally desired. 3. Posted online and available to the public. Oct 2024. Continuing to add information.
7/1/24- 9/30/24 | Program Director | Website Contact | Maintain SREC website as Communication vehicle. | Ongoing | 1. Ongoing
7/1/24- 9/30/24 | Program Director Recruiter | Teal Street | 1. Continued development of the Navigational Tool. 2. Work with clients at Teal Street Center through walk-in or by appointment. Support education/employment referral and assistance with benefits. 3. Dedicated Navigator activities to locate regional events and/or services for posting on the Navi Tool and SREC website. | 1. Until complete, Target by 8/30/24 2. Start once trained 3. Ongoing | 1.Ongoing. 2. Weekly scheduled office hours were observed at Teal Street Center. Community accessing support very limited. 3. Posted new services and community activities to websites and provided time during coalition meeting for notice and discussion.
7/1/24- 9/30/24 | Program Director | Summit | 1. Confirm speakers and venders by 9/30/24. 2. Have brochures created with class scheduling to be handed out at event. 3. Have orientation packets put together for event. 4. Gathered Door prizes from DBA, if applicable. 5. Have computers/printer ready for set up at event for finalizing class certifications. 6. Have Relais set up in Navi tool with roll out available for Summit. CPR First Aid. DSP courses | 1. By 9/30/24 2. By 9/30/24 3. By 9/30/24 4. By 9/30/24 5. By 9/30/24 6. By 9/30/24 | 1-6 completed Summit was successful community event
7/1/24- 9/30/24 | Program Director | Senior Centers | 1. Coordinate CPR Training and skills check, (Relais) 2. Develop collaborative effort to create a Triage Navigational Training for Senior Center Staff. 3. Purchase Tablets and establish plan for video conferencing equipment. 4. Set-up plan for data collection by staff. | 1. By 8/30/24, however rolling out with Summit, 2. Complete by 9/30/2024. 3. Based on availability of technology available. 3. Set up meeting with Erin Walker-Tolles by 8/30/24. | 1. CPR and First aid offered to Senior Center staff at the Summit - completed 2. Delayed at this time. Tablets will not be purchased due to challenges being faced by Senior Center staff with setting up technology. Tablets have been utilized previosuly at the Senior Centers without sucess. 4. Working to develop data collection plan with Erin Walker-Tolles, CCS.
7/1/24-9/30/24 | Program Director | UAS | 1. Meet with APCA for additional funding and partnership. 2. Meet with UAS on funding needs. 3. Meet with Riverview for support for CNA courses to be offered and developed in Juneau with contract associated with funding. 4. Determine if village delivery of courses is possible to offer additional students opportunities. 5. Statewide Survey for DSDS Certification course for marketing for UAS. | 1. 7/30/24 2. 7/30/24 3.7/30/24 4. 9/30/24 5. 7/15/24 | 1. APCA stated that they would help with funding and then delayed responses. In short they are willing to help only if people apply directly to them for assistance. They are not sharing funding with the SREC project and the relationship outlined in the orginal grant agreement, never existed. 2. Meeting conducted in July with follow up in Oct. Meeting occurred with Challenor's' Office in October with follow up meeting between UAS and SEARHC/Bartlett. Spring courses are scheduled and planned to occur for CNA offers. 3. Pended or possible disregard based on status of UAS and other collaborative needs. 4. Village delivery options have been reviewed and shared with UAS. Follow up has been attempted but no responses. 5. Survey sent out in December, limited responses.
7/1/24-9/30/24 | Program Director | E-Modification | 1. Meeting with Mental Health Trust. 2. Meeting with SAIL. 3. Develop possible pilot or determine if a project could be developed to assist in process. - possible meeting with construction unions/contractors. 4. Look for resources to add to Navi tool for home modification. 5. Look for additional funding, | 1. 9/30/24 2. 9/30/24 3. Ongoing 4. Ongoing 5. Ongoing | 1. Meet with Kelda Barstad of the Mental Health Trust , DSDS is hiring staff to start to work on the program from the state to federal level. 2. several meeting with SAIL. They are monitoring the interactions with DSDS and meeting to discussion some options. DSDS has rolled out modification funding that is not Medicaid supported. 3. Developed list of regional contractors, researching construction process in each community. 4. Added contraction list to Navi Tool and continuing to look for more information. 5. Ongoing. Mental Health Trust may have funding to support a pilot, would need to apply.
2nd QRT FY25
10/1/2024-12/31/2024 | Program Director | Wage Supplementation | 1. Change wage supplement to financial retention incentives. 2. Conduct quick research with regional/ companies to determine total DSP staff available. 3. Draft application for support. 4. Determine total funding to back service. | 1. ongoing 2. Email sent out to local agencies some quick to respond others taking more time. 3. Draft application created. 4. Pending for further discussion. | 1. ongoing 2. Email sent out to local agencies some quick to respond others taking more time. 3. Draft application created. 4. Pending for further discussion.
10/1/24- 12/31/24 | Program Director | Summit | 1. Final preparations for Summit 2. Create survey for participants 3. Media Push for Summit - Radio, email, social media 4. Post photo contest participants on the Navi Tool and SREC website. 5. Plan and organize SC Annual Retreat. | 1. 9/30/24 2. 9/30/24 3. 9/30/24 4. 9/30/24 5. 12/16/2024 | 1,3 Accomplished. 2. Survey features utilities during the conference and comment cards provided at the event. 3. Katelyn worked on media coverage through social media and radio. Video and radio announcements completed. 4. Did not occur. No entries were made to the photo contest that could be utilized. 5. SC had Annual meeting Dec 2024. Program Director, updated documents supporting the Coalition. Secretary duties are now placed back onto the SREC program staff.
10/1/24- 12/31/24 | Program Director | Website Contact | Maintain SREC website as Communication vehicle. | Ongoing | Monthly maintain, ongoing
10/1/24- 12/31/24 | Program Director Recruiter | Teal Street | 1. Work with clients at Teal Street Center through walk-in or by appointment. Support education/employment referral and assistance with benefits. 2. Duties to be assigned for Summit. 3. Report on success / proposed modifications of processes for Coalition. 4. Dedicated Navigator activities to locate regional events and/or services for posting on the Navi Tool and SREC website | 1. Ongoing 2. 9/31/2024 3. Report weekly to Program Director 4. Plan to be developed by 12/31/24. | 1. 2025 Closed Teal Street office in November 2024 due to lack of community interest and effort to save funding for more productive activities. 2. Completed 3. Update provided to SREC Nov 2024, monthly report conducted 4. ongoing additions being made.
10/1/24- 12/31/24 | Program Director | Senior Center | 1. Encourage establishment of paid caregiver support groups. 2. Assist with Media coverage to participate (social media, flyers, and emails to coalition) 3. Promote at Summit. | 1. Ongoing 2. Ongoing, once dates and times can be established 3. Promote through Navi Tool presentation. | 1. CCS has caregiver support available to the community. 2. Delayed, Senior Centers are not ready to move forward with navigation. They have received My Senior Center software to better manage their data collection and time. The set up has taken longer than expected. We have been meeting monthly. SREC staff have been assisting with changes to be made on the Intake forms for CCS to create additional data driven information. 3. SC and JEDC Leadership declined to promote Navi Tool the Summit.
3rd QRT FY 25
12/31/24- 3/31/25 | Program Director | Program Management | 1. Present Fiscal Year End Report to Coalition Steering Committee and recommendation for Year Three Work Plan. 2. Review budget for addition objectives and activities to be determined via strategic planning and assessment of activities. (possible small Summit, additional training, DPS picnic.). 3. SC voted to change duties and placed Secretary duties back on SREC staff. | 1. TBA 2. By 2/1/25 3. SREC Project staff to take over Secretary Duties | 1. Updated this document for Workplan for Jan 2025. Last update was June 2024. 2. Working to develop a plan for a resource fair in Sitka for March 2025. 3. SC voted to place Secretary duties back onto the SREC staff to manage for the coalition. Updated all documents associated with the SREC coalition.
12/31/24- 3/31/25 | Program Director | Website Contact | Maintain SREC website as Communication vehicle. | Ongoing | Ongoing, monthly
12/31/24- 3/31/25 | Recruiter | Navi Tool Resource Fair | 1. Continue dedicated Recruiter activities using all available resources, emphasizing DSP Recruitment. Identifying job fairs and local events to promote workforce. 2. Report on success / proposed modifications of processes for Coalition 3. Recruiter will post job opening on Navi Tool and Website, social media etc. 4. Developed plan for Resource Fair in Sitka | 1. Ongoing 2. Report weekly to Program Director 3. Weekly review | 1. Tess will continue to provide information to the SREC on upcoming events. 2. Remove, intended for recruitment process from original plan. 3. Job opening are posted on NAVI tool. 4. Met with Sitka Tribe who is willing to share lunch day in March for Resource fairs. Tess is starting to coordinate with the Centennial Hall in Sitka to start process to plan for event. Vendor request list has been created to coordinate with community providers once venue can be secured.
12/31/24- 3/31/25 | Program Director | Navi Tool Resource Fair | 1. Report on success / proposed modifications of processes for Coalition. 2. Dedicated Navigator activities to locate regional events and/or services for posting on the Navi Tool and SREC website. 3. Begin planning Ketchikan Resource Fair. | 1. Ongoing 2. Ongoing 3. Ongoing TBA Dates | 1. Monthly report provided to SREC. 2. ongoing adding additional resources to NAVI tool 3. Sent email seeking venue in Ketchikan Dec 2024. They are in full support of having the event at the Plaza Mall. Looking at 9/12/25 as possible date.
12/31/24- 3/31/25 | Program Director | Senior Center | 1. Encourage establishment of paid caregiver support groups. 2. Assist with Media coverage to participate (social media, flyers, and emails to coalition) 3. Senior Center staff support for questions and navigational guidance. 4. Weekly Training | 1. Ongoing 2. Ongoing, once dates and times can be established 3. Ongoing 4. Ongoing | 1. Caregiver support to be provided by Case Managers. 2. Templates created. Senior Centers have not been ready to open to the pubic with navigational supports due to long time delayed with onboarding My Senior Center. 3. SREC staff have engaged Senior Center staff weekly for 1 hour training since October 2024. 4. Ongoing
4th QRT FY 25
4/1/25- 6/30/25 | Program Director | Program Management Resource Fair | 1. Report monthly to the Steering Committee on progress. 2. Assisted with design and implementation of Resource Fair 3. Assist with coordination of activities, Resource fairs 4. Provide secretary duties to SREC | 1. Monthly reporting to the Steering Committee 2. Delivery date by March 6 2025 Sitka, Ketchikan TBA (9/12/25) 3. Delivery date by March 6 2025 Sitka, Ketchikan TBA (9/12/25) 4. Ongoing
4/1/25- 6/30/25 | Program Director | Website Contact | Maintain SREC website as Communication vehicle. | Ongoing
4/1/25- 6/30/25 | Recruiter | Navi tool Resource Fairs | 1. Continue dedicated Recruiter activities using all available resources, emphasizing DSP Recruitment. Identifying job fairs and local events to promote workforce. 2. Report on success / proposed modifications of processes for Coalition 3. Recruiter will post job opening on Navi Tool and Website, social media etc. | 1. Ongoing 2. Report weekly to Program Director 3. Weekly review
4/1/25-6/30/25 | Program Director | Resource Fair | 1. Continued development and planning for a resource fair in Ketchikan. 2. Review budget for Spring 2026 Summit in Juneau. Start to develop plan. | 1. Ongoing with date TBA. 2. Determine venue and costs, plan accordingly
4/1/25- 6/30/25 | Program Director | NAVI Tool | 1. Report on success / proposed modifications of processes for Coalition. 2. Dedicated Navigator activities to locate regional events and/or services for posting on the Navi Tool and SREC website. | 1. Report weekly to Program Director 2. Ongoing
4/1/25- 6/30/25 | Program Director | Senior Center | 1. Encourage establishment of paid caregiver support groups. 2. Assist with Media coverage to participate (social media, flyers, and emails to coalition) 3. Weekly Training | 1. Ongoing 2. Ongoing 3. Ongoing until 12/25
1st QRT FY 26
7/1/25 - 9/30/25 | Program Director | Program Management Data collection | 1. Present Fiscal Year End Report to Coalition Steering Committee. 2. Review of data collection by Senior Centers and Research Team 3. Seek additional funding 4. Provide secretary duties to SREC | 1. TBA 2. Ongoing 3. Ongoing 4. Ongoing
7/1/25- 9/30/25 | Program Director | Website Contact | 1. Maintain SREC website as Communication vehicle. 2. Determine if the Steering Committee is wanting to continue with the website and who and how the website should be continued to be maintained long term for the coalition. | 1. Ongoing 2. Meet with the Steering Committee by 7/15/25
7/1/25- 9/30/25 | Recruiter | Navi Tool Resource Fair | 1. Continue dedicated Recruiter activities using all available resources, emphasizing DSP Recruitment. Identifying job fairs and local events to promote workforce. 2. Report on success / proposed modifications of processes for Coalition 3. Members to submit staffing positions to Recruiter for all levels of positions. Recruiter will post job opening on Navi Tool and Website, social media etc. 4. Implement Ketchikan Resource fair. 5. Planning for Summit 2026 Juneau. | 1. Ongoing 2. Report weekly to Program Director 3. Weekly review 4. Fall Venue TBA 5. TBA
7/1/25-9/30/25 | Program Director | Senior Centers | 1. Support Senior Center staff in providing a Triage Navigational program and activities. 2. Review data collection | 1. ongoing 2. by 9/30/25
7/1/25- 9/30/25 | Program Director | Navi Tool | 1. Report on success / proposed modifications of processes for Coalition. 2. Dedicated Navigator activities to locate regional events and/or services for posting on the Navi Tool and SREC website | 1. Report weekly to Program Director 2. Ongoing
2nd QRT FY 26
10/1/25- 12/31/25 | Program Director | Senior Centers | 1. Review Data to be collected and received. 2. Post to website, data findings. | 1. 9/30/25 2. 12/31/25
10/1/25-12/31/25 | Recruiter | Navi Tool Resource Summit Juneau | 1. Report on success / proposed modifications of processes for Coalition. 2. Dedicated Navigator activities to locate regional events and/or services for posting on the Navi Tool and SREC website 3. Continued planning for Summit Juneau Spring 2026. | 1. Ongoing 2. Report weekly to Program Director 3. TBA
3rd QRT FY 26
12/31/25-3/31/26 | Program Director | Program Management | 1. Finalize fiscal year needs and reporting 2. Summarize project and findings in deliverable document | 1. TBA 2. TBA
4th QRT FY 26
3/31/26-6/30/26 | Program Director | Website Contact | 1. Maintain SREC website as Communication vehicle. 2. Determine if the Steering Committee is wanting to continue with the website and who and how the website should be continued to be maintained long term for the coalition. | 1. Ongoing 2. Meet with the Steering Committee by 7/15/25, implement plan and move management of the website to another agency or individual. Train them to manage on going.
3/31/26-6/30/26 | Recruiter | Program management | 1. Final Report to the Coalition | 1. TBA 2. TBA
3/31/26-6/30/26 | Program Director | Program Management | 1. Finalize fiscal year needs and reporting 2. Summarize project and findings in deliverable document | 1. TBA 2. TBA